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Data-center white-space build-out
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Racks, pathways, cabling, labels, access, and technology turnover, coordinated with the electrical, cooling, grounding, structural, fire, and security work owned by the responsible trades.
Intended outcome
Cabinet positions, pathways, labels, port plans, and open facility dependencies checked against a rack-ready checklist.
Service scope
White space is the controlled area occupied by IT cabinets and their supporting distribution. A successful build-out coordinates technology with architectural, structural, electrical, mechanical, fire-protection and security scopes.
GHT’s role is defined at the project boundary: racks, pathways, cabling, labeling, technology coordination and documentation may be included, while licensed facility work is performed by and verified through the designated trades.
How the system fits together
	01  Cabinet row
	Equipment locations, rack units, weight and service clearances

	02  Connectivity plane
	Overhead or underfloor pathways and distribution zones

	03  Facility plane
	Power, bonding, cooling, fire and structural dependencies

	04  Operations plane
	Access, labeling, monitoring and change-control handoff


Typical project triggers
•  New rows or cages are being added
•  Power or cooling density changes with a hardware refresh
•  Overhead and underfloor routes compete for space
•  Cabinet delivery is ahead of documented readiness
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Delivery and acceptance
Revision 1.0   •   06 September 2026   •   2 / 3
The final project scope identifies quantities, locations, dependencies, and the evidence required at each delivery stage.
01  Basis of design
Confirm cabinet schedule, loads, topology, density, resilience and owner/colo standards.
Acceptance evidence: Requirements matrix and responsibility boundary
02  Multidiscipline layout
Coordinate elevations, aisles, clearances, pathways, power feeds, airflow and security zones.
Acceptance evidence: Coordinated rack/pathway plan and issue log
03  Install and stage
Set approved technology infrastructure, labels and patching in the agreed construction sequence.
Acceptance evidence: Installation inspection sheets and progress photos
04  Readiness turnover
Verify cabinet, path, port, power and facility dependencies before equipment activation.
Acceptance evidence: Rack-ready checklist, as-builts and open-item register
Handover deliverables
•  Coordinated rack and pathway layout
•  Cabinet/rack-ready checklist
•  Technology responsibility matrix
•  Label, port and patching schedule
•  As-built elevations, photos and open-item log
Closeout: GHT and the customer review the agreed evidence, record unresolved exceptions and owners, and confirm acceptance against the signed project scope.
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Planning and scope boundaries
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Customer and site inputs
•  Cabinet, rack-unit, weight and delivery schedule
•  Power feed, redundancy and load information
•  Cooling design and expected IT heat load
•  Network topology and cable-density forecast
•  Security, fire, access and construction sequence
Constraints and coordination
•  Facility work owned by licensed/designated trades
•  Floor loading, anchorage and service clearances
•  Power/cooling availability and commissioning sequence
•  Live-room access, contamination control and change management
Commercial scope and responsibilities
This specification describes the service framework. The signed statement of work defines included equipment, quantities, software licenses, integrations, access windows, schedule, pricing, warranty, and support coverage. Additional construction, electrical work, recurring subscriptions, and ongoing support require an explicit line item.
The customer appoints an acceptance owner and provides authorized access, required site information, and decisions. GHT records assumptions, coordinates assigned work, and submits changes for agreement before expanding the scope.
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